**Level 6**

**Unit Specialist Practice**

**Work Planning**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Week /Date** | **Scheduled Session** | **List of Jobs** | **What I plan to Achieve** | **Contingency and Evaluation** |
|  |  |  |  |  |
| Week 1  Tuesday  29/9/15 | 10am-12.30pm  1.30- 4.30pm  6pm | First day back at Uni.  PI project launch.  Start brainstorming ideas. | * Brainstorm ides for SP * Start thinking about how I can approach PI. | ✓  ✓ |
| Week 1  Wednesday  30/9/15 | 10 am- 1.30pm  3pm | SP project launch.  Launch PI website | * Launch PI website * Contact someone to help with professional logo. | ✓  ✓ |
| Week 1  Thursday  1/10/15 | Independent  Study  11am-4pm  4.30pm- 9.30pm | Launch SP website  Working at River Island | * Launch SP website * Look into student services lectures to help personal development. * Unable to work after 4pm | ✓  ✓  ✓ |
| Week 1  Friday  2/10/15 | 10am- 12.30pm  1.30pm-4.30pm  5.30pm – 9pm | Designing Bespoke Postiche Project Realities and Possibilities.  The project proposal and study plan.  Working at River Island | * After work focus on the tutorial aims given after tutorial Friday afternoon. | X – No tutorial was given to me Friday afternoon as time ran out- however tutorial rescheduled for Tuesday afternoon. |

**Level 6**

**Unit Specialist Practice**

**Work Planning**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Week /Date** | **Scheduled Session** | **List of Jobs** | **What I plan to Achieve** | **Contingency and Evaluation** |
| Week 1  Saturday  3/10/15 | Work all day | Part Time river island. | Think about design ideas. | ✓ |
| Week 1  Sunday  4/10/15 | Work all day | Part Time River Island. | Think about design ideas. | ✓ |
| Week 2  Monday  5/10/15 | All day | Catch up on any lesson write up. | Begin thinking about research areas and technical aspects of work. | ✓ |
| Week 2  Tuesday  6/10/15 | 10am- 12:30pm  1:30pm- 4:30pm | Avant Garde Hair frames.  Airbrushing Recap. | Begin researching into hair aspects that may influence my work. | ✓ |
| Week 2  Wednesday  7/10/15 | All day | London Trip | Try to focus on areas that may be of interest to project. | ✓ |

**Level 6**

**Unit Specialist Practice**

**Work Planning**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Week /Date** | **Scheduled Session** | **List of Jobs** | **What I plan to Achieve** | **Contingency and Evaluation** |
| Week 2  Thursday  8/10/15 | Work all day at River Island | Research | Start researching wig companies and hair suppliers. | ✓ |
| Week 2  Friday  9/10/15 | 9:30am- 1:30pm  1:30pm- 4:30pm | Sculpting workshop  Prosthetics Q&A | Write up | Was unwell this day and was not able to attend university, spent the day at home after doctors. |
| Week 2  Saturday  10/10/15 | Work at river island 11am- 7:30pm | Evening research. | Research into animals and adaptations etc. to inspire work. | ✓- Did not achieve as much research as work made me feel more ill throughout the day so found it difficult to concentrate. |
| Week 2  Sunday  11/10/15 | All day | Study Plan | Start study plan and think about an overarching theme of work and what I hope to achieve. | ✓ |
| Week 3  Monday  12/10/15 | All day | Contingency Time | Finish Study Plan | ✓ - Finished study plan in contingency time. |

**Level 6**

**Unit Specialist Practice**

**Work Planning**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Week /Date** | **Scheduled Session** | **List of Jobs** | **What I plan to Achieve** | **Contingency and Evaluation** |
| Week 3  Tuesday  13/10/15 | 10am-12.30pm  1.30pm- 4.30pm  5.30pm- 10pm | * Tutorials and presenting project plans. * Imagining the demonic. * Website work | Feedback from project plan- try and go over points tonight and write on blog.  Website work- write up previous lessons and document collaboration. | ✓ |
| Week 3  Wednesday  14/10/15 | 9.30- 4.30pm  7pm- 11pm | * Dissertation brief and launch. * Website work continuing from Tuesday. | Write up dissertation brief info.  Continue to write up lessons and collaboration. |  |
| Week 3  Thursday  15/10/15 | 10am- 4pm  5pm- 9.30pm | * Website work. * Work at River Island | Write up brief research and inspiration images.  Think about wig templates and hair to later create a starting point. |  |
| Week 3  Friday  16/10/15 | 10am -12.30pm  1.30pm- 4.30pm  6pm-9pm | * Practical workshop. * Imagining the demonic. * Catch up time. | Time in the evening for catch up on anything that has not been achieved throughout the week. |  |
| Week 3  Saturday  17/10/15 | AWAY FOR  WEEKEND |  |  |  |

**Level 6**

**Unit Specialist Practice**

**Work Planning**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Week /Date** | **Scheduled Session** | **List of Jobs** | **What I plan to Achieve** | **Contingency and Evaluation** |
| Week 3  Sunday  18/10/15 | AWAY FOR WEEKEND | Look at:  BY hair  Stranded  Puk | Sunday eve- look at hair companies and document. | ✓  Hair Companies researched and written on blog |
|  |  |  |  |  |
| Week 4  Monday  19/10/15 | 9am -12.30pm  12:30- 1:30pm  2pm- 10pm | Talk from Christian Mallett.  Attend Student Services Dissertation planning.  Buy hair and materials ready for wig/ sculpture. | Attend Talk and Write up.  Dissertation talk have ideas thought through ready for student services work shop. | ✓  Dissertation talk at lunch time with student services extremely helpful allowed me to figure out the topics and structure of my writing.  X - Had a talk with Carolyne decided not to buy the hair as I am thinking of making wefts instead of wig- needs extended thought. |
| Week 4  Tuesday  20/10/15 | 10-1:30 pm  1:30- 4:30 pm  5:30- 9pm | Creature Design  History of Hair  Tutorial with Carolyne  Work at River Island | Attend Lectures Throughout the day.  Work in the evening- After prepare for fashion shoot Wednesday. | Busy day managed to prepare for fashion shoot tomorrow after work this evening. |
| Week 4  Wednesday  21/10/15 | 10am-7pm Roughly  9pm-10pm | Fashion Editorial collaboration shoot with other AUB students.  Make a small amount of time for thinking about dissertation before tutorials Thursday. | Make a small amount of time for thinking about dissertation before tutorials Thursday. | The shoot was a long day since there was 8 different looks to shoot on set.  ✓  Travelling home took some time out of my evening however I did think about the tutorials Thursday and thought about possible case studies. |
| Week 4  Thursday  22/10/15 | 11am-3pm  5pm-9.30pm  9.30pm -? | Tutorials with Jon and Amanda  Work at River Island  Make final edits to project plan and work plan. | In between tutorials go to library and look at possible relevant books for dissertation.  Final edits to project and work plan after part time job. | ✓  X – Did not get back from work until later, needed a good sleep so I could have a longer day Friday. |
|  |  |  |  |  |

**Level 6**

**Unit Specialist Practice**

**Work Planning**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Week /Date** | **Scheduled Session** | **List of Jobs** | **What I plan to Achieve** | **Contingency and Evaluation** |
| Week 4  Friday  23/10/15 | 9:30am- 10am  10am- 12:30pm  1:30pm-4:30pm  5:30pm- 10pm | MA tutorial (surgery time)  Lecture: The cosmetic advertisement semiotic analysis  Tech dem lead session.  Library time to catch up on some website work. | Think about MA courses and look at Portsmouth university MA’s also.  Make sure work plan and study plan are complete and sent.  Write up lesson from today and start on uploading some contextual research. | ✓  ✓ |
| Week 4  Saturday +  Sunday 24th/ 25th/10/15 | Working all weekend! | Website work. | I hope to write up a majority of lessons that are not already on blog as I will not have a huge amount of time over the weekend. | ✓ |
| Week 5  Monday  26/10/15 | Contingency Time | Contingency Time | Catch up on anything not achieved the past week and perhaps fit in some additional research time. | Busy this day so did not catch up on that much. |
| Week 5  Tuesday  27/10/15 | 10am- 12:30pm  1:30pm- 4:30pm  Evening | Lecture: From page to stage.  Developing Practical research and experimentation.  Library time | Lectures throughout the day.  In library time I hope to develop my research and write up lessons from that day. | ✓ |
| Week 5  Wednesday  28/10/15 | 10am-12:30pm  Afternoon and Evening | Sculpture workshop.  Library Session | Spend time in the library researching hair textures and materials- part wigs, wefts instead of full wig to avoid.  Research wig constructions.  Order hair. | Library internet was down could not use it on my laptop.  Held off of ordering hair as model was changing. |

**Level 6**

**Unit Specialist Practice**

**Work Planning**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Week /Date** | **Scheduled Session** | **List of Jobs** | **What I plan to Achieve** | **Contingency and Evaluation** |
| Week 5  Thursday  29/10/15 | All day | Buy materials for wig construction  Research | Additional research to inform wig constructions, start thinking about exact place these images will be seen/advertised. | X – project changed no longer wig construction  Held off on products |
| Week 5  Friday  30/10/15 | 10am- 12:30pm  1:30pm- 4:30pm  Evening | Practical Workshop  Wig Workshop | Make majority of wefts for the hair. | X again had not ordered hair as model was changing. |
| Week 5  Saturday &  Sunday  31/10/15 &  1/10/15 | Working all weekend  Contingency time | Working at River Island  Contingency time | Contingency time used around work to catch up on anything I have missed or not achieved. | ✓ |
|  |  |  |  |  |
|  |  |  |  |  |

**Level 6**

**Unit Specialist Practice**

**Work Planning**

|  |  |  |  |
| --- | --- | --- | --- |
| **Week /Date** | **Scheduled Session** | **List of Jobs**  **What I plan to Achieve** | **Contingency and Evaluation** |
| Week 6  02/11/15- 08/11/15 | 9:30- 4:30  Tuesday  Thursday  Friday –  Scheduled in Time.  River Island Part Time  Thursday 5:30- 9:30pm  Saturday 11- 7:30pm  Free days – Monday Wednesday Sunday | Draw up some designs and discuss benefits and problems with all to inform final decision with hair structure.  Research starting Investigative Study then write introduction (dissertation)  Continue Wefting and start Creating Hair structure.  Focus on research informing practical developments.  Write up informing research as I go depending on variations in design. | ✓  ✓  ✓  ✓  x |
|  |  |  |  |

**Level 6**

**Unit Specialist Practice**

**Work Planning**

|  |  |  |  |
| --- | --- | --- | --- |
| **Week /Date** | **Scheduled Session** | **List of Jobs**  **What I plan to Achieve** | **Contingency and Evaluation** |
| Week 7  09/11/15-  15/11/15 | Surgery tutorials  Monday  Scheduled sessions:  9:30- 4:30pm  Tuesday  Wednesday  Friday  River Island Part Time  Thursday 5:30- 9:30pm  Saturday 11- 7:30pm | One section of Investigative Study (dissertation).  Continue creating Hair Sculpture.  Make any changes to design aspects as I continue to create the hair structure. | ✓  ✓  ✓  Unwell disrupting practical, dissertation. |

**Level 6**

**Unit Specialist Practice**

**Work Planning**

|  |  |  |  |
| --- | --- | --- | --- |
| **Week /Date** | **Scheduled Session** | **List of Jobs**  **What I plan to Achieve** | **Contingency and Evaluation** |
| Week 8  16/11/15-  22/11/15 | Scheduled time  9:30- 4:30  Monday  Tuesday  Wednesday  Friday  Work part time River Island contracted hours.  Thursday 5:30- 9:30pm  Saturday 11am- 7:30pm | Section Two Investigative Study (Dissertation) written.  Part of section 3 written.    Make Up tests.  Hair Tests. | ✓  ✓  ✓  Unwell disrupting practical |

**Level 6**

**Unit Specialist Practice**

**Work Planning**

|  |  |  |  |
| --- | --- | --- | --- |
| **Week /Date** | **Scheduled Session** | **List of Jobs**  **What I plan to Achieve** | **Contingency and Evaluation** |
| Week 9  23/11/15- 29/11/15 | Scheduled time:  9:30-4:30pm  Tuesday  Wednesday  Friday  Work part time River Island contracted hours.  Thursday 5:30- 9:30pm  Saturday 11am- 7:30pm | Third part of dissertation written and conclusion. Ready for draft hand in wed 25/11/15.  Hair Completed | X did not complete dissertation as was very ill for past few weeks |

**Level 6**

**Unit Specialist Practice**

**Work Planning**

|  |  |  |  |
| --- | --- | --- | --- |
| **Week /Date** | **Scheduled Session** | **List of Jobs**  **What I plan to Achieve** | **Contingency and Evaluation** |
| Week 10  30/11/15-  06/12/15 | Scheduled time:  9:30-4:30pm  Wednesday  Friday  Work part time River Island contracted hours.  Thursday 5:30- 9:30pm  Saturday 11am- 7:30pm | Almost all blog research written up and completed so far.  Test Shoot  Write up test shoot.  Begin writing critical evaluation.  Any changes to design to be made now. | X had more blog to do than first thought as this came with additional research  X did not do a test shoot  ✓  Did begin evaluation  Finalised design |

**Level 6**

**Unit Specialist Practice**

**Work Planning**

|  |  |  |  |
| --- | --- | --- | --- |
| **Week /Date** | **Scheduled Session** | **List of Jobs**  **What I plan to Achieve** | **Contingency and Evaluation** |
| Week 11  07/12/15-  13/12/15 | Scheduled time:  9:30-4:30pm  Tuesday  Wednesday  Friday  Work part time River Island contracted hours.  Thursday 5:30- 9:30pm  Saturday 11am- 7:30pm | Final Shoot  Photographers editing time.  Write up final shoots and evaluations.  Write majority of critical evaluation. | ✓  ✓  x- did not write up shoots as photographer had her hand in and I will not receive the images for a couple weeks.  Completed shoot |

**Level 6**

**Unit Specialist Practice**

**Work Planning**

|  |  |  |  |
| --- | --- | --- | --- |
| **Week /Date** | **Scheduled Session** | **List of Jobs**  **What I plan to Achieve** | **Contingency and Evaluation** |
| Week 12  14/12/15-  20/12/15 | Scheduled time:  9:30-4:30pm  Thurs/Friday  Draft feedback for dissertation.  Work part time River Island contracted hours.  Thursday 5:30- 9:30pm  Saturday 11am- 7:30pm | Aim to finish project apart from final images and final critical evaluation.  Focus on dissertation and re writing/ improving it.  This will allow me to focus over Christmas getting my dissertation to a really good stage.  Dissertation research completely done. | X did not finish everything by this point was still waiting for images and edited images.  X have not focused on dissertation in this week.  Had time off over Christmas but worked at river island for a lot of the break. |

**Level 6**

**Unit Specialist Practice**

**Work Planning**

|  |  |  |  |
| --- | --- | --- | --- |
| **Week /Date** | **Scheduled Session** | **List of Jobs**  **What I plan to Achieve** | **Contingency and Evaluation** |
| Week 13  05/01/16-  10/01/16 | Scheduled Time:  Hand in Tuesday week 13 by 12pm.  Wed, Thursday & Friday 9:30-4:30pm.  Work part time River Island contracted hours.  Thursday 5:30- 9:30pm  Saturday 11am- 7:30pm | Print Final Portfolio Images before this point.  Final edits to website and last steps.  Hand in Tuesday 06/01/16. | ✓  Printed final photos in final week  ✓  ✓  Was difficult to balance work and hand in pressures but I am satisfied with the level of work on my blog and final images. |

**Level 6**

**Unit Professional Identity (After SP hand In)**

**Work Planning**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Week /Date** | **Scheduled Session** | **List of Jobs** | **What I plan to Achieve** | **Contingency and Evaluation** |
| Week 14  11/01/16- 17/01/16 | Work Thurs eve, Saturday and Sunday at River Island. | Research colour themes and begin thinking about logo styles | Contact someone to help with logo | ✓ |
| Week 15  18/01/16- 24/01/16 | Wednesday 20th  Friday 21st  Work Thurs eve, Saturday and Sunday at River Island. | Foam latex recap and troubleshooting  Continuity and on set etiquette | Meet with graphic design student to set up business card/ logo design. | ✓ |
| Week 16  25/01/16- 31/01/16 | Work Thurs eve, Saturday and Sunday at River Island. | Research website makers | Pay for domain and website for professional purposes | ✓ |
| Week 17  01/02/15- 07/02/16 | Thursday 4th  Work Thurs eve, Saturday and Sunday at River Island. | Preparing for professional presentations/ interview. Written evaluations, content and structure. | Look at business card styles  Order business cards  Begin building website | ✓  x- Could not decide on style and logo was not finished.  ✓ |
| Week 18  08/02/16-14/02/16 | Friday 13th  Work Thurs eve, Saturday and Sunday at River Island. | Show reel editing | Decide on logo and branding style  Order business cards  Begin presentation | ✓  ✓  ✓ |
| Week 19  15/02/16- 21/02/16 | Work Thurs eve, Saturday and Sunday at River Island. | Promotional material | Sort out CV  Print portfolio images  Create presentation | ✓  ✓  ✓ |
| Week 20  22/02/16- 28/02/16 | Monday 22nd  Tuesday 25th  Wednesday 24th  Work Thurs eve, Saturday and Sunday at River Island. | Finish promotional material  Finish presentation for interview  Professional Interview day | Get business cards, CV, website and portfolio finished.  Finish off presentation for interview and print out all needed documents  Complete interview | ✓  ✓  ✓ |
| Week 21  29/02/16- 06/03/16 | Work Thurs eve, Saturday and Sunday at River Island. | Reflect on interview | Work on developmental website  Begin thinking about improvements after interview | x- Was demotivated after interview did not achieve this. |
| Week 22  07/03/16- 13/03/1 | Work Thurs eve, Saturday and Sunday at River Island. | Contingency time for week 21 | Contingency time for week 21 | ✓ - only because I changed work plan to catch up. |
| Week 23  14/03/16- 20/03/16 | Work Thurs eve, Saturday and Sunday at River Island. | Personal Development plan | Finish personal development plan | x- Almost finished but not quite. |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Week 24  21/03/16-27/03/16 | Work Thurs eve, Saturday and Sunday at River Island. | Research week for development website. | Research for development.  Finish PDP | ✓  ✓ |
| Week 25  28/03/16- 03/04/16 | Work Thurs eve, Saturday and Sunday at River Island. | Watch interview video | Watch interview video and critically reflect | x- could not get video, video had been sent to my trash folder and I did not receive it |
| Week 26  04/04/16- 10/04/16 | Work Thurs eve, Saturday and Sunday at River Island. | Promotional | Re- order business cards to higher standard.  Complete 500 words of critical report | ✓  x- still had not seen video |
| Week 27  11/04/16- 17/04/16 | Wednesday 13th  Work Thurs eve, Saturday and Sunday at River Island. | Final PI tutorial. | Get feedback from tutorial and edit anything changed or discussed in tutorial  Complete 1,000 words of critical report | ✓  ✓ - began without watching video. |
| Week 28  18/04/16-24/04/16 | Tuesday 19th  Wednesday 20th  Work Thurs eve, Saturday and Sunday at River Island. | Finish Critical Report  Hand in PI before 12pm | Last look over interview video and finish 1,500 words.  Hand in body of work to faculty office. | ✓ - Finally got hold of the file and was able to finish and go over critical report.  ✓ |